## Project
IT3M HUMCOMP-Human Computer Interaction
Group 5 - GANTT CHART
Group Google Meet Link
PROJECT TITLE: Vulcanizing Shop Management System Design
PROJECT LEADER: SAPINOSO, Maritoni Joy
GROUP MEMBERS: DELA CRUZ, Renz V.
MAGSINO, Jericho E.
OHOYLAN, Alvin S.
ORLANDA, Harold L.
Task Deliverables | Task Assigned | Scheduled Start Date | Scheduled End Date | Actual Start Date | Actual End Date | Duration | Status | Remarks | Comment | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04
1. PROJECT PLANNING
1.1 Research | All | 2025-08-30 |  | 2025-09-06 |  | 19 | 50% | In Progress |  | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress
1.2 Brainstorming | All | 2025-08-30 |  | 2025-09-06 |  | 19 | 50% | In Progress |  | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress
1.3 Beneficiary Selection | All | 2025-08-30 | 2025-09-06 | 2025-09-06 | 2025-09-06 | 0 | 100% | Done | Beneficiary Details | Done | Done | Done | Done | Done | Done | Done | Done
1.4 Interview Questionnaire and Form | Dela Cruz, Magsino, Sapinoso | 2025-09-18 |  | 2025-09-18 |  | 7 | 75% | In Progress | Interview Questions | [19 empty] | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress
1.5 Consent Form/ Request Letter | Dela Cruz, Magsino, Sapinoso | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 0 | 100% | Done | Request Letter Unsigned | [14 empty] | Done
1.6 Research Proposal | All | 2025-09-23 |  | 2025-09-23 |  | 2 | 25% | In Progress | Research Proposal | [24 empty] | In Progress | In Progress | In Progress
1.7 Project Title Formulation | Magsino | 2025-09-18 | 2025-09-23 | 2025-09-18 | 2025-09-23 | 5 | 100% | Done | [20 empty] | Done | Done | Done | Done | Done | Done
2. DATA GATHERING
2.1 Invitation/Interview | Orlanda
2.2 Interview Logging/Recording | Ohoylan
2.3 Data Validation/Review | All
2.4 Data Analysis | All
3. PROJECT DESIGN
3.1 High Level Design
3.2 Medium Level Design
3.3 Low Level Design
4. PRESENTATION
4.1 Title Presentation | All | 2025-09-23 |  | 2025-09-23 |  | 2 | 25% | In Progress | Title PPT | [24 empty] | In Progress | In Progress | In Progress

## Group Activities
IT3M HUMCOMP-Human Computer Interaction
Group 5 - GANTT CHART
Group Leader: SAPINOSO, Maritoni Joy
Group Members: DELA CRUZ, Renz V.
MAGSINO, Jericho E.
OHOYLAN, Alvin S.
ORLANDA, Harold L.
Task Deliverables | Task Assigned | Scheduled Start Date | Scheduled End Date | Actual Start Date | Actual End Date | Duration | Status | Remarks | Comment | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22
Activity #1: Research | All | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 0 | 100% | Completed | Team effort | Completed
Activity #1: Presentation/Delivery | Ohoylan | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 0 | 100% | Completed | Delivered Successfully | Completed
Activity #2: Research | All | 2025-08-23 | 2025-08-30 | 2025-08-23 | 2025-08-28 | 5 | 100% | Completed | Team effort | [7 empty] | Completed | Completed | Completed | Completed | Completed | Completed
Activity #2: PPT | Magsino, Sapinoso | 2025-08-23 | 2025-08-30 | 2025-08-23 | 2025-08-28 | 5 | 100% | Completed | Activity 2 | [7 empty] | Completed | Completed | Completed | Completed | Completed | Completed
Activity #3: Research | All | 2025-08-23 | 2025-08-30 | 2025-08-23 | 2025-08-27 | 4 | 100% | Completed | Team effort | [7 empty] | Completed | Completed | Completed | Completed | Completed
Activity #3: PPT | Sapinoso | 2025-08-23 | 2025-08-30 | 2025-08-23 | 2025-08-27 | 4 | 100% | Completed | Activity 3 | [7 empty] | Completed | Completed | Completed | Completed | Completed
Gantt Chart | Sapinoso | 2025-08-30 | 2025-09-06 | 2025-08-30 | 2025-09-06 | 7 | 100% | Completed | Updating | [14 empty] | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed